USBVault Enterprise

Production Readiness Sprint Plan

4 Sprints  |  8 Weeks  |  72 Audit Findings  →  Production Ready

| Date | March 23, 2026 |
| --- | --- |
| Team | 1–2 Engineers (Full-Stack) |
| Sprint Length | 2 weeks each |
| Total Duration | 8 weeks (March 24 – May 15, 2026) |
| Source | Full Engineering Audit (6 plugin analysis) |
| Goal | Production deployment with zero critical findings |

# 1. Sprint Plan Overview

This plan decomposes all 72 findings from the full engineering audit into 4 focused sprints. Each sprint has a single clear goal, a prioritized backlog, and explicit success criteria. Items are sequenced to maximize safety: cryptographic and security fixes first, then stability, then quality and polish.

## 1.1 Sprint Timeline

| Sprint | Theme | Dates | Goal |
| --- | --- | --- | --- |
| Sprint 1 | Crypto & Security Foundation | Mar 24 – Apr 4 | Fix all CRITICAL crypto and security findings |
| Sprint 2 | Server Stability & Auth Hardening | Apr 7 – Apr 18 | Eliminate resource leaks, race conditions, auth gaps |
| Sprint 3 | Client Quality & Testing | Apr 21 – May 2 | Frontend resilience, test coverage, documentation |
| Sprint 4 | Deploy Readiness & Hardening | May 5 – May 15 | Infrastructure, monitoring, launch checklist, burn-in |

## 1.2 Capacity Planning

With 1–2 full-stack engineers at 70–80% capacity (accounting for interrupts, code review, and context switching), each 2-week sprint provides approximately 7–8 productive engineering days per person. Items are estimated in story points where 1 point ≈ half a day of focused work for one engineer.

| Sprint | Available Days | Capacity (pts) | Planned (pts) | Load % | Buffer For |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | 14–16 | 28–32 | 26 | 81–93% | Crypto complexity |
| Sprint 2 | 14–16 | 28–32 | 24 | 75–86% | Race condition debugging |
| Sprint 3 | 14–16 | 28–32 | 22 | 69–79% | Test writing overhead |
| Sprint 4 | 14–16 | 28–32 | 20 | 63–71% | Infra provisioning delays |

Sprint 4 is deliberately lighter to absorb any overflow from earlier sprints and to provide time for the 7-day staging burn-in period required before production deployment.

Sprint 1: Crypto & Security Foundation March 24 – April 4, 2026 ¦ 26 points planned

Sprint Goal: Eliminate every cryptographic vulnerability and critical security gap. After this sprint, the zero-knowledge guarantee is provably intact and all E2E encryption paths are sound.

## Sprint 1 Backlog

| Pri | ID | Task | File | Pts | Area |
| --- | --- | --- | --- | --- | --- |
| P0 | C-2 | Replace XOR nonce derivation with HKDF-Expand in streaming.rs | streaming.rs:149-156 | 5 | Crypto |
| P0 | CR-5 | Validate X25519 shared secret length before KDF | sharing.rs:139 | 2 | Crypto |
| P0 | CR-1 | Fix AES-256-GCM nonce size mismatch in XChaCha20 context | streaming.rs:194 | 3 | Crypto |
| P0 | CR-3 | Add mutex protection to global JWT key variables | jwt.go:46-49 | 2 | Security |
| P0 | CR-2 | Validate Redis state schema in SRP verify handler | srp.go:220 | 2 | Security |
| P0 | TD-1 | Replace TODO certificate pinning placeholders with real pins | certificatePinning.ts | 2 | Security |
| P0 | H-7 | Remove unsafe-inline and unsafe-eval from Electron CSP | main.ts:56-59 | 3 | Security |
| P0 | H-8 | Add IPC handler input validation + path traversal guard | usb-ipc-adapter.ts | 3 | Security |
| P1 | CR-4 | Make token refresh promise assignment atomic | api.ts:162-166 | 2 | Auth |
| P1 | H-1* | Validate SRP ephemeral key range check (1 < a < N) | srp_client.rs:172 | 2 | Crypto |

Verification Criteria

- All existing crypto fuzz targets pass (cargo fuzz run cipher, streaming, sharing, vault_header, kdf — 10 min each)

- New property test: HKDF-derived nonces are unique for any 2 chunk indices under same base nonce

- New test: sealed-box roundtrip with wrong secret key fails

- Electron CSP audit: no unsafe-inline or unsafe-eval in production build

- IPC fuzzing: path traversal payloads (../../etc/passwd) rejected in all 14 handlers

- JWT key rotation test passes under 100 concurrent goroutines

Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| HKDF nonce change breaks existing encrypted files | Data loss for existing vaults | Write migration tool that re-derives nonces; test on copy of prod data first |
| SRP range check breaks login on older clients | Users locked out | Feature-flag the check; validate client version before enforcing |

Sprint 2: Server Stability & Auth Hardening April 7 – April 18, 2026 ¦ 24 points planned

Sprint Goal: Eliminate all resource leaks, race conditions, and server-side stability risks. After this sprint, the server can run indefinitely under load without memory growth or connection exhaustion.

## Sprint 2 Backlog

| Pri | ID | Task | File | Pts | Area |
| --- | --- | --- | --- | --- | --- |
| P0 | C-3 | Make vault rollback check atomic (single UPDATE WHERE) | repository.go:231-256 | 2 | Server |
| P0 | C-4 | Fix WebSocket read loop goroutine leak | sync/service.go:233-253 | 3 | Server |
| P0 | C-5 | Check Stripe decode error + close response body | billing/service.go:372 | 1 | Server |
| P0 | H-5 | Fix X-Forwarded-For to use rightmost untrusted IP | middleware/auth.go:251-270 | 2 | Security |
| P0 | H-6 | Fix rate limit fallback to use limit/instanceCount | ratelimit.go:210-219 | 2 | Security |
| P0 | M-7 | Close HTTP response body in device attestation | attestation.go:472-479 | 1 | Server |
| P0 | M-8 | Preserve trace context in async audit goroutine | audit.go:86-119 | 2 | Observability |
| P1 | H-3 | Clean up all background processes on logout | authStore.ts:298-326 | 3 | App |
| P1 | H-4 | Store and call Zustand unsubscribe handles | syncStore.ts, offlineStore.ts | 2 | App |
| P1 | M-6 | Add hard pagination cap (1000) at repository layer | repository.go:74-103 | 1 | Server |
| P1 | TD-2 | Add HTTP timeout for Stripe API client | billing/service.go:145-149 | 1 | Server |
| P1 | TD-3 | Validate uuid.Parse return in CreateVault | vault/service.go:96 | 1 | Server |
| P2 | M-9 | Restrict K8s egress to known destinations only | production-values.yaml | 3 | Infra |

Verification Criteria

- Goroutine leak test: 1000 WebSocket connect/disconnect cycles, goroutine count returns to baseline

- Rollback race test: 50 concurrent vault update requests with same version, exactly 1 succeeds

- Memory stability: 4-hour soak test with simulated load, RSS stays within 20% of baseline

- Logout cleanup: after logout, zero timers/intervals active, zero API calls in network tab

- Rate limit: X-Forwarded-For spoofing test with forged header returns 429 within limits

- Stripe timeout: mock 30s-hung endpoint, request fails within configured timeout

Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Atomic rollback SQL change breaks existing migrations | Server won't start | Test migration on staging DB snapshot before merging |
| WebSocket deadline change causes premature disconnects | Sync interruptions | Set generous deadline (60s) with heartbeat refresh every 15s |
| Egress policy blocks legitimate outbound traffic | Stripe/S3 failures | Enumerate all outbound IPs first; deploy with monitoring only before enforcing |

Sprint 3: Client Quality & Testing April 21 – May 2, 2026 ¦ 22 points planned

Sprint Goal: Harden the client app against edge cases, close the biggest test coverage gaps, and fill critical documentation holes. After this sprint, the app handles degraded network, empty states, and large datasets gracefully.

## Sprint 3 Backlog

| Pri | ID | Task | File(s) | Pts | Area |
| --- | --- | --- | --- | --- | --- |
| P0 | M-1 | Add Zod schema validation for critical API responses | api.ts:355-379 | 3 | App |
| P0 | M-2 | Add AbortController to all useEffect API calls | app/(tabs)/*.tsx | 2 | App |
| P0 | M-5 | Implement cursor-based pagination for vault list | vaultListStore.ts + API | 4 | Full-stack |
| P1 | M-3 | Pause activity polling when tab/app backgrounded | activity.tsx:105-110 | 1 | App |
| P1 | M-4 | Stop metadata batch timer on logout | metadataReductionService.ts | 1 | App |
| P1 | TEST-1 | Add Electron desktop smoke test suite (10+ tests) | electron-shell/ | 3 | Testing |
| P1 | TEST-2 | Expand component test coverage to 15+ components | usbvault-app/src/components/ | 3 | Testing |
| P1 | DOC-1 | Write usb-companion README + API documentation | usb-companion/ | 2 | Docs |
| P1 | DOC-2 | Document WebSocket sync protocol (message formats, flows) | docs/api/ | 2 | Docs |
| P2 | TD-4 | Remove 80+ console.log/console.error from production code | usbvault-app/src/ | 1 | Cleanup |

Verification Criteria

- API response validation: malformed server response triggers user-friendly error, not crash

- Pagination: vault list renders 500+ vaults without memory spike (FlatList windowing active)

- Component coverage: jest --coverage reports 60%+ for usbvault-app/src/components/

- Electron tests: npm test in electron-shell passes 10+ smoke tests covering IPC, CSP, tray

- usb-companion README exists with setup, API reference, and protocol description

- Console cleanup: grep -r console.log src/components/ returns 0 results

Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Pagination API change breaks existing mobile clients | App shows empty vault list | Version the API endpoint; old clients fall back to unpaginated |
| Zod validation too strict, rejects valid responses | False-positive error screens | Start with warn-only mode; promote to hard failure after 1 week |

Sprint 4: Deploy Readiness & Production Hardening May 5 – May 15, 2026 ¦ 20 points planned

Sprint Goal: Complete every item on the launch checklist, execute a 7-day staging burn-in, and be ready for production traffic. After this sprint, we deploy.

## Sprint 4 Backlog

| Pri | ID | Task | Target | Pts | Area |
| --- | --- | --- | --- | --- | --- |
| P0 | LAUNCH-1 | Provision production PostgreSQL RDS (encrypted, Multi-AZ) | Infrastructure | 2 | Infra |
| P0 | LAUNCH-2 | Provision Redis ElastiCache + S3 bucket | Infrastructure | 2 | Infra |
| P0 | LAUNCH-3 | Configure DNS, TLS cert, and production secrets in K8s | Infrastructure | 2 | Infra |
| P0 | LAUNCH-4 | Fill rollback trigger thresholds in launch checklist | LAUNCH_CHECKLIST.md | 1 | Process |
| P0 | LAUNCH-5 | Add env validation to release pipeline (CI gate) | release.yml | 2 | CI/CD |
| P0 | LAUNCH-6 | Configure Sentry DSN for production | sentry.ts + sentry.go | 1 | Monitoring |
| P0 | LAUNCH-7 | Configure Stripe live webhook secret | Production env | 1 | Billing |
| P1 | LAUNCH-8 | Test database backup + restore procedure in staging | runbooks/01-database-recovery.md | 2 | DR |
| P1 | LAUNCH-9 | Remove hardcoded dev credentials from docker-compose.yml | docker-compose.yml | 1 | Security |
| P1 | TD-5 | Clean up _dead_code/ directory and main.go.bak | Multiple files | 1 | Cleanup |
| P1 | DOC-3 | Publish privacy policy and terms of service | docs/legal/ | 1 | Legal |
| P1 | LAUNCH-10 | Run 7-day staging burn-in with synthetic load | Staging environment | 4 | Validation |

Verification Criteria

- All 39 verified + 19 blocked items on LAUNCH_CHECKLIST.md are checked off

- Staging burn-in: 7 consecutive days with <0.1% error rate, no memory growth, no goroutine leaks

- Backup restore tested: RDS snapshot restore completes within 30 minutes (RTO target)

- All 7 Prometheus alert rules fire correctly when thresholds are exceeded

- Rollback procedure tested: deploy, detect anomaly, rollback completes in <5 minutes

- Privacy policy and terms of service published and linked from app + landing page

Burn-In Monitoring Checklist

| Metric | Threshold | Alert | Action |
| --- | --- | --- | --- |
| API error rate (5xx) | < 0.1% | APIHighErrorRate | Investigate + rollback if > 1% |
| p99 latency | < 500ms | APIHighLatency | Profile slow endpoints |
| Goroutine count | Stable ±10% | Custom | Check for leak regression |
| Memory RSS | Stable ±20% | PodMemoryHigh | Restart + investigate |
| Database connections | < 80% pool | DBConnectionPoolExhausted | Check connection leaks |
| Redis hit rate | > 90% | Custom | Review cache keys |
| Cert expiry | > 30 days | SSLCertExpiringSoon | Rotate certificate |

# 3. Dependencies & Sequencing

This section maps critical dependencies between items to prevent sequencing mistakes.

## 3.1 Hard Dependencies (Must Be Sequential)

| Prerequisite | Dependent | Why |
| --- | --- | --- |
| C-2 (HKDF nonces) | All streaming tests | New nonce scheme must be in place before any integration test |
| Sprint 1 crypto fixes | Sprint 3 pagination | Pagination changes must not break crypto integration |
| Sprint 2 server stability | Sprint 4 burn-in | Server must be leak-free before burn-in is meaningful |
| LAUNCH-1,2,3 (infra) | LAUNCH-10 (burn-in) | Infrastructure must exist before burn-in starts |
| TD-1 (cert pins) | LAUNCH-3 (TLS) | Real cert pins require the production TLS certificate |

## 3.2 Items That Can Be Parallelized

- Sprint 1: Crypto fixes (Rust) can be done in parallel with Electron security fixes (TypeScript) by different engineers

- Sprint 2: Server-side fixes (Go) can be done in parallel with client-side cleanup (TypeScript)

- Sprint 3: Test writing can happen in parallel with documentation writing

- Sprint 4: Infrastructure provisioning can happen while legal docs are finalized

# 4. Definition of Done

Every item in every sprint must meet ALL of the following criteria before being marked complete:

| Category | Criteria |
| --- | --- |
| Code | Code reviewed by at least 1 other engineer (or self-reviewed with 24h cooling period for solo dev) |
| Tests | New code has unit tests. Bug fixes have regression tests that fail without the fix. |
| CI | All CI checks pass: linter, type checker, tests, security scans (Semgrep, gosec, cargo-audit) |
| Docs | If the change affects API surface, user behavior, or deployment: documentation updated |
| Verification | Sprint-specific verification criteria (listed per sprint above) satisfied |
| No Regressions | Full test suite passes. No new warnings in CI output. |

# 5. Sprint Ceremonies & Checkpoints

Even with a small team, lightweight ceremonies keep momentum visible and catch issues early.

| Ceremony | When | Duration | Purpose |
| --- | --- | --- | --- |
| Sprint Planning | Day 1 | 1 hour | Review backlog, assign items, identify unknowns |
| Daily Check-in | Daily | 10 min (async OK) | Progress update, blockers, help needed |
| Mid-Sprint Review | Day 5 | 30 min | Check P0 progress, re-prioritize if needed, cut scope if behind |
| Sprint Demo | Day 9 | 30 min | Show completed work, run verification tests live |
| Sprint Retro | Day 10 | 30 min | What worked, what didn't, what to change next sprint |

## 5.1 Escalation Triggers

If any of the following occur, escalate immediately rather than waiting for the next ceremony:

- A P0 item is blocked for more than 4 hours

- A crypto fix reveals a deeper architectural issue than expected

- Mid-sprint review shows <50% of P0 items complete

- Any security finding is discovered that wasn't in the original audit

# 6. Complete Item Tracker

Master list of all 45 items across 4 sprints, for tracking in your project management tool of choice.

| Sprt | Pri | ID | Task | Pts | Area | Status |
| --- | --- | --- | --- | --- | --- | --- |
| S1 | P0 | C-2 | Replace XOR nonce derivation with HKDF-Expand in streaming.rs | 5 | Crypto | ☐ Not Started |
| S1 | P0 | CR-5 | Validate X25519 shared secret length before KDF | 2 | Crypto | ☐ Not Started |
| S1 | P0 | CR-1 | Fix AES-256-GCM nonce size mismatch in XChaCha20 context | 3 | Crypto | ☐ Not Started |
| S1 | P0 | CR-3 | Add mutex protection to global JWT key variables | 2 | Security | ☐ Not Started |
| S1 | P0 | CR-2 | Validate Redis state schema in SRP verify handler | 2 | Security | ☐ Not Started |
| S1 | P0 | TD-1 | Replace TODO certificate pinning placeholders with real pins | 2 | Security | ☐ Not Started |
| S1 | P0 | H-7 | Remove unsafe-inline and unsafe-eval from Electron CSP | 3 | Security | ☐ Not Started |
| S1 | P0 | H-8 | Add IPC handler input validation + path traversal guard | 3 | Security | ☐ Not Started |
| S1 | P1 | CR-4 | Make token refresh promise assignment atomic | 2 | Auth | ☐ Not Started |
| S1 | P1 | H-1* | Validate SRP ephemeral key range check (1 < a < N) | 2 | Crypto | ☐ Not Started |
| S2 | P0 | C-3 | Make vault rollback check atomic (single UPDATE WHERE) | 2 | Server | ☐ Not Started |
| S2 | P0 | C-4 | Fix WebSocket read loop goroutine leak | 3 | Server | ☐ Not Started |
| S2 | P0 | C-5 | Check Stripe decode error + close response body | 1 | Server | ☐ Not Started |
| S2 | P0 | H-5 | Fix X-Forwarded-For to use rightmost untrusted IP | 2 | Security | ☐ Not Started |
| S2 | P0 | H-6 | Fix rate limit fallback to use limit/instanceCount | 2 | Security | ☐ Not Started |
| S2 | P0 | M-7 | Close HTTP response body in device attestation | 1 | Server | ☐ Not Started |
| S2 | P0 | M-8 | Preserve trace context in async audit goroutine | 2 | Observability | ☐ Not Started |
| S2 | P1 | H-3 | Clean up all background processes on logout | 3 | App | ☐ Not Started |
| S2 | P1 | H-4 | Store and call Zustand unsubscribe handles | 2 | App | ☐ Not Started |
| S2 | P1 | M-6 | Add hard pagination cap (1000) at repository layer | 1 | Server | ☐ Not Started |
| S2 | P1 | TD-2 | Add HTTP timeout for Stripe API client | 1 | Server | ☐ Not Started |
| S2 | P1 | TD-3 | Validate uuid.Parse return in CreateVault | 1 | Server | ☐ Not Started |
| S2 | P2 | M-9 | Restrict K8s egress to known destinations only | 3 | Infra | ☐ Not Started |
| S3 | P0 | M-1 | Add Zod schema validation for critical API responses | 3 | App | ☐ Not Started |
| S3 | P0 | M-2 | Add AbortController to all useEffect API calls | 2 | App | ☐ Not Started |
| S3 | P0 | M-5 | Implement cursor-based pagination for vault list | 4 | Full-stack | ☐ Not Started |
| S3 | P1 | M-3 | Pause activity polling when tab/app backgrounded | 1 | App | ☐ Not Started |
| S3 | P1 | M-4 | Stop metadata batch timer on logout | 1 | App | ☐ Not Started |
| S3 | P1 | TEST-1 | Add Electron desktop smoke test suite (10+ tests) | 3 | Testing | ☐ Not Started |
| S3 | P1 | TEST-2 | Expand component test coverage to 15+ components | 3 | Testing | ☐ Not Started |
| S3 | P1 | DOC-1 | Write usb-companion README + API documentation | 2 | Docs | ☐ Not Started |
| S3 | P1 | DOC-2 | Document WebSocket sync protocol (message formats, flows) | 2 | Docs | ☐ Not Started |
| S3 | P2 | TD-4 | Remove 80+ console.log/console.error from production code | 1 | Cleanup | ☐ Not Started |
| S4 | P0 | LAUNCH-1 | Provision production PostgreSQL RDS (encrypted, Multi-AZ) | 2 | Infra | ☐ Not Started |
| S4 | P0 | LAUNCH-2 | Provision Redis ElastiCache + S3 bucket | 2 | Infra | ☐ Not Started |
| S4 | P0 | LAUNCH-3 | Configure DNS, TLS cert, and production secrets in K8s | 2 | Infra | ☐ Not Started |
| S4 | P0 | LAUNCH-4 | Fill rollback trigger thresholds in launch checklist | 1 | Process | ☐ Not Started |
| S4 | P0 | LAUNCH-5 | Add env validation to release pipeline (CI gate) | 2 | CI/CD | ☐ Not Started |
| S4 | P0 | LAUNCH-6 | Configure Sentry DSN for production | 1 | Monitoring | ☐ Not Started |
| S4 | P0 | LAUNCH-7 | Configure Stripe live webhook secret | 1 | Billing | ☐ Not Started |
| S4 | P1 | LAUNCH-8 | Test database backup + restore procedure in staging | 2 | DR | ☐ Not Started |
| S4 | P1 | LAUNCH-9 | Remove hardcoded dev credentials from docker-compose.yml | 1 | Security | ☐ Not Started |
| S4 | P1 | TD-5 | Clean up _dead_code/ directory and main.go.bak | 1 | Cleanup | ☐ Not Started |
| S4 | P1 | DOC-3 | Publish privacy policy and terms of service | 1 | Legal | ☐ Not Started |
| S4 | P1 | LAUNCH-10 | Run 7-day staging burn-in with synthetic load | 4 | Validation | ☐ Not Started |

# 7. Post-Launch Backlog (Beyond Sprint 4)

These items are important but not blocking production. They form the backlog for the next planning cycle after launch.

## 7.1 Strategic Improvements

- Complete repository pattern across all domains (VaultRepo, SharingRepo, AuditRepo, BillingRepo)

- External audit of custom Shamir's Secret Sharing implementation (shamir.rs)

- Implement canary deployment strategy (Flagger or Argo Rollouts)

- Automated rollback based on Prometheus metrics (error rate threshold)

- Database roles with least-privilege grants (app, backup, readonly)

- Process isolation for Rust crypto FFI (run in subprocess instead of in-process)

## 7.2 Quality & Polish

- Expand component test coverage from 60% to 80%+

- Add performance benchmarks for all critical paths (Argon2id, streaming cipher, API latency)

- Accessibility audit (screen reader, keyboard nav, color contrast per WCAG 2.1 AA)

- Complete OpenAPI spec with endpoint-by-endpoint examples and rate limit docs

- Database schema documentation with ERD diagram

## 7.3 Feature Roadmap (from FUTURE_PHASES_TODO.md)

- Phase 6: V3.0 Cloud Split-Key for true zero-trust (~10 days)

- Phase 7: V4.0 Advanced Security — steganography, security tiers, duress password (~15 days)

- Phase 8: Launch Readiness — app store submissions, enterprise packaging (~5 days)