# USBVault Enterprise

Updated Production Readiness Sprint Plan

Incorporating Data Plugin Analysis Findings

March 23, 2026

# Sprint Overview

| Sprint | Dates | Original Pts | Added Pts | Total Pts |
| --- | --- | --- | --- | --- |
| Sprint 1 | Mar 24 - Apr 4 | 26 | 0 | 26 |
| Sprint 2 | Apr 7 - Apr 18 | 24 | 0 | 24 |
| Sprint 3 | Apr 21 - May 2 | 22 | 10 | 32 |
| Sprint 4 | May 5 - May 15 | 20 | 7 | 27 |

Total project scope: 109 points across 8 weeks

# New Findings from Data Analysis

The following 7 items emerged from data plugin analysis and were not in the original architecture review. They are integrated into Sprint 3 and Sprint 4 as noted.

## USB-COMP-1: USB Companion Vendored Node.js Binaries (NEW)

Severity: CRITICAL

- 359 MB of compiled binaries in git (darwin-arm64 + darwin-x64 Node.js installs)

- Includes npm, corepack, headers, docs — none needed at runtime

- Darwin-only, not portable despite 'portable app' goals

- Fix: .gitignore node/ directory, create scripts/fetch-node.sh for build-time downloads

- Impact: Massive git repository bloat, cloning delays

## TEST-GAP-1: Frontend Test Coverage Critically Low (NEW)

Severity: HIGH

- usbvault-app: ~393 source files, ~1% test coverage

- Go backend: 72% coverage — major imbalance creates risk

- Fix: Auth flows, crypto bridge, vault operations must have integration test coverage

- Impact: Regressions in critical paths hard to catch

## MONO-1: Five Monolithic Files >1000 LOC (NEW)

Severity: MEDIUM

- classroom.tsx (1,854 LOC), messaging.ts (1,129 LOC), sharing.ts (1,024 LOC)

- Strong correlation (r=0.996) between file size and TODO count

- Impact: Tech debt accelerant, harder to maintain and test

## I18N-1: Misaligned Locale Files (NEW)

Severity: LOW

- Paywall strings in de/es/fr locales, missing from en.json

- Fix: Sync all locale files for consistency

## BUS-1: Single-Author Codebase — Knowledge Risk (NEW)

Severity: MEDIUM (Process)

- All commits from one author; no enforced code review practice

- Fix: Document architecture decisions, create onboarding, establish PR workflow

## DEP-1: 301 External Dependencies (NEW)

Severity: MEDIUM (Supply Chain)

- No lockfile integrity checks or version pinning discipline

- Fix: Add npm audit + cargo audit to CI, generate SBOM

## REPO-1: Committed Static Build Artifacts (NEW)

Severity: LOW

- usb-companion/static/ contains pre-built JS bundle + assets (23 MB)

- Fix: Build from source in CI, .gitignore static/

# Sprint 1: Crypto & Security Foundation

Mar 24 - Apr 4  |  26 points  |  Status: PLANNING

## Sprint Goal

Establish cryptographic primitives, key derivation, and secure secret storage foundation. No new findings — sprint scope UNCHANGED from original plan.

## Backlog

| Pr | ID | Task | Files | Pts | Area | Sts |
| --- | --- | --- | --- | --- | --- | --- |
| P1 | C-1 | PBKDF2 key derivation | usb-vault-core/ | 3 | Crypto | TODO |
| P1 | C-2 | AES-256-GCM encryption | usb-vault-core/ | 4 | Crypto | TODO |
| P1 | C-3 | Secret rotation + version | usb-vault-core/ | 3 | Crypto | TODO |
| P2 | C-4 | Secure RNG | usb-vault-core/ | 2 | Crypto | TODO |
| P2 | C-5 | Crypto test vectors | usb-vault-core/tests/ | 3 | Crypto | TODO |
| P1 | H-1 | Hash function + HMAC | usb-vault-core/ | 2 | Crypto | TODO |
| P1 | H-2 | Password strength | usb-vault-core/ | 2 | Security | TODO |
| P2 | H-3 | Rate limiting | usb-vault-core/ | 2 | Security | TODO |
| P2 | H-4 | Audit logging | usb-vault-core/ | 2 | Logging | TODO |
| P2 | H-5 | TLS hardening | server/ | 2 | Security | TODO |

## Verification Criteria

- All crypto modules pass test vectors

- No hardcoded secrets in code

- TLS ciphers validated against OWASP Top 10

## Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Weak PBKDF2 params | Brute-force vulnerability | Enforce min 600k iterations; peer review |
| Key leakage in logs | Secret compromise | Audit log output; sanitize traces |
| Incomplete test coverage | Undiscovered crypto flaw | Require test vectors for each |

# Sprint 2: Server Stability & Auth Hardening

Apr 7 - Apr 18  |  24 points  |  Status: PLANNING

## Sprint Goal

Harden authentication, implement server-side session management, and stabilize core API endpoints. No new findings — sprint scope UNCHANGED.

## Backlog

| Pr | ID | Task | Files | Pts | Area | Sts |
| --- | --- | --- | --- | --- | --- | --- |
| P1 | M-1 | OAuth 2.0 / OIDC | server/auth/ | 4 | Auth | TODO |
| P1 | M-2 | Session token mgmt | server/session/ | 3 | Auth | TODO |
| P1 | M-3 | Vault CRUD API | server/api/ | 3 | API | TODO |
| P1 | M-4 | MFA (TOTP/SMS) | server/mfa/ | 4 | Auth | TODO |
| P2 | M-5 | Database schema | server/db/ | 2 | Database | TODO |
| P2 | M-6 | Error handling | server/ | 2 | Stability | TODO |
| P2 | M-7 | Monitoring + alerts | server/ | 2 | Ops | TODO |
| P2 | M-8 | Load testing | server/tests/ | 2 | Perf | TODO |
| P1 | M-9 | CSRF/SSRF protection | server/ | 2 | Security | TODO |

## Verification Criteria

- OAuth 2.0 flow with external provider

- Session tokens expire correctly

- 100+ concurrent users without degradation

- All error messages redacted

## Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Session fixation attacks | Unauthorized access | Regenerate ID on login; short TTL |
| MFA bypass via SMS | Account takeover | Enforce TOTP; SMS fallback only |
| DB pool exhaustion | Service outage | Set max pool size; circuit breaker |

# Sprint 3: Client Quality & Testing

Apr 21 - May 2  |  32 points (original 22 + 10 new)  |  Status: PLANNING

## Sprint Goal

Elevate frontend test coverage, remove repository bloat, refactor monolithic files, and ensure production-grade client quality. Integrate 5 new findings.

## Backlog (Existing + New)

| Pr | ID | Task | Files | Pts | Area | Sts |
| --- | --- | --- | --- | --- | --- | --- |
| P1 | CR-1 | Component library | usbvault-app/ | 3 | FE | TODO |
| P1 | CR-2 | Form validation | usbvault-app/forms/ | 3 | FE | TODO |
| P2 | CR-3 | Theme system | usbvault-app/theme/ | 2 | FE | TODO |
| P2 | CR-4 | A11y audit | usbvault-app/ | 2 | FE | TODO |
| P2 | CR-5 | Mobile responsive | usbvault-app/ | 2 | FE | TODO |
| P2 | TD-1 | TS strict mode | usbvault-app/ | 2 | Quality | TODO |
| P2 | TD-2 | ESLint+Prettier | usbvault-app/ | 1 | Quality | TODO |
| P1 | TD-3 | Dependency audit | usbvault-app/ | 2 | Quality | TODO |
| P2 | TD-4 | Unused code | usbvault-app/ | 2 | Quality | TODO |
| P1 | TEST-2* | Component tests | usbvault-app/tests/ | 5 | Testing | TODO |
| P1 | USB-COMP-1 | Remove Node bins | usb-companion/ | 3 | Build | TODO |
| P2 | MONO-1 | Decompose mono | usbvault-app/ | 4 | Refactor | TODO |
| P2 | I18N-1 | Sync locales | locales/ | 1 | i18n | TODO |
| P2 | REPO-1 | Remove artifacts | usb-companion/ | 2 | Build | TODO |

* TEST-2 upgraded from 3 to 5 pts

## Verification Criteria

- Git repo size reduced by >350 MB

- Component tests cover auth, vault ops, crypto (coverage: 1% -> 15%)

- No file >1000 LOC in src/

- All locale files have identical key sets

- TypeScript strict mode passes

## Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Remove Node breaks build | CI/CD failure | Test fetch-node.sh thoroughly |
| Refactoring introduces bugs | Regressions | Component tests ensure parity |
| Locale sync misses keys | UX broken | Automated key validation in CI |
| Aggressive refactor delays | Scope creep | Time-box; prioritize classroom.tsx |

# Sprint 4: Deploy Readiness & Production Hardening

May 5 - May 15  |  27 points (original 20 + 7 new)  |  Status: PLANNING

## Sprint Goal

Expand frontend test coverage to critical flows, harden supply chain, and prepare for production launch. Integrate 3 new findings.

## Backlog (Existing + New)

| Pr | ID | Task | Files | Pts | Area | Sts |
| --- | --- | --- | --- | --- | --- | --- |
| P1 | LAUNCH-1 | Deployment playbook | docs/ops/ | 2 | Ops | TODO |
| P1 | LAUNCH-2 | Secrets mgmt | server/config/ | 2 | Ops | TODO |
| P1 | LAUNCH-3 | Health checks | server/ | 2 | Ops | TODO |
| P2 | LAUNCH-4 | Graceful shutdown | server/ | 2 | Ops | TODO |
| P2 | LAUNCH-5 | Prometheus metrics | server/metrics/ | 2 | Ops | TODO |
| P2 | LAUNCH-6 | Log aggregation | server/ | 1 | Ops | TODO |
| P1 | LAUNCH-7 | SAST/DAST | CI/ | 2 | Security | TODO |
| P1 | LAUNCH-8 | Pen test scope | docs/security/ | 2 | Security | TODO |
| P2 | LAUNCH-9 | Incident response | docs/ops/ | 1 | Ops | TODO |
| P2 | LAUNCH-10 | Post-launch handoff | docs/ | 2 | Ops | TODO |
| P1 | TEST-GAP-2 | Integration tests | usbvault-app/tests/ | 3 | Testing | TODO |
| P1 | BUS-1 | Arch docs + onb | docs/arch/ | 2 | Docs | TODO |
| P1 | DEP-1 | Supply chain hard | CI/ | 2 | Security | TODO |

## Verification Criteria

- Integration tests: auth, vault ops, crypto bridge

- Frontend coverage: 1% -> 20%+ (critical paths)

- npm audit + cargo audit in CI; zero critical vulns

- SBOM generated; versions pinned

- Architecture documented for 5+ components

- Onboarding enables new contributor setup <2hrs

## Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Integration tests too broad | Maintenance burden | Focus on happy + edge cases |
| Single-author knowledge persists | Bus factor unchanged | Pair on architecture docs |
| Dependency audit finds critical | Last-minute fix | Run audit early; budget 1wk fix |
| Pen test reveals bypass | Launch delay | Start scoping early; 1wk buffer |

# Complete Item Tracker

All 55 items across 4 sprints. NEW items are marked.

| Sprint | Proj | ID | Task | Files | Pts | Area |
| --- | --- | --- | --- | --- | --- | --- |
| S1 | Crypto | C-1 | PBKDF2 | usb-vault-core/ | 3 | Crypto |
| S1 | Crypto | C-2 | AES-256-GCM | usb-vault-core/ | 4 | Crypto |
| S1 | Crypto | C-3 | Secret rotation | usb-vault-core/ | 3 | Crypto |
| S1 | Crypto | C-4 | Secure RNG | usb-vault-core/ | 2 | Crypto |
| S1 | Crypto | C-5 | Test vectors | usb-vault-core/tests/ | 3 | Crypto |
| S1 | Hash | H-1 | Hash + HMAC | usb-vault-core/ | 2 | Crypto |
| S1 | Hash | H-2 | Password strength | usb-vault-core/ | 2 | Security |
| S1 | Hash | H-3 | Rate limiting | usb-vault-core/ | 2 | Security |
| S1 | Hash | H-4 | Audit logging | usb-vault-core/ | 2 | Logging |
| S1 | Hash | H-5 | TLS hardening | server/ | 2 | Security |
| S2 | Main | M-1 | OAuth 2.0 | server/auth/ | 4 | Auth |
| S2 | Main | M-2 | Session mgmt | server/session/ | 3 | Auth |
| S2 | Main | M-3 | Vault CRUD | server/api/ | 3 | API |
| S2 | Main | M-4 | MFA | server/mfa/ | 4 | Auth |
| S2 | Main | M-5 | DB schema | server/db/ | 2 | DB |
| S2 | Main | M-6 | Error handling | server/ | 2 | Stability |
| S2 | Main | M-7 | Monitoring | server/ | 2 | Ops |
| S2 | Main | M-8 | Load test | server/tests/ | 2 | Perf |
| S2 | Main | M-9 | CSRF/SSRF | server/ | 2 | Security |
| S3 | Client | CR-1 | Comp. library | usbvault-app/ | 3 | Frontend |
| S3 | Client | CR-2 | Form valid. | usbvault-app/ | 3 | Frontend |
| S3 | Client | CR-3 | Theme | usbvault-app/ | 2 | Frontend |
| S3 | Client | CR-4 | A11y | usbvault-app/ | 2 | Frontend |
| S3 | Client | CR-5 | Mobile | usbvault-app/ | 2 | Frontend |
| S3 | Tech | TD-1 | TS strict | usbvault-app/ | 2 | Quality |
| S3 | Tech | TD-2 | Lint | usbvault-app/ | 1 | Quality |
| S3 | Tech | TD-3 | Deps audit | usbvault-app/ | 2 | Quality |
| S3 | Tech | TD-4 | Dead code | usbvault-app/ | 2 | Quality |
| S3 | Test | TEST-2* | Component tests | usbvault-app/ | 5 | Testing |
| S3 | Build | USB-COMP-1* | No Node bins | usb-companion/ | 3 | Build |
| S3 | Refactor | MONO-1* | Decompose | usbvault-app/ | 4 | Refactor |
| S3 | i18n | I18N-1* | Sync locales | locales/ | 1 | i18n |
| S3 | Build | REPO-1* | No artifacts | usb-companion/ | 2 | Build |
| S4 | Deploy | LAUNCH-1 | Playbook | docs/ops/ | 2 | Ops |
| S4 | Deploy | LAUNCH-2 | Secrets | server/config/ | 2 | Ops |
| S4 | Deploy | LAUNCH-3 | Health chk | server/ | 2 | Ops |
| S4 | Deploy | LAUNCH-4 | Shutdown | server/ | 2 | Ops |
| S4 | Deploy | LAUNCH-5 | Prometheus | server/ | 2 | Ops |
| S4 | Deploy | LAUNCH-6 | Logs | server/ | 1 | Ops |
| S4 | Security | LAUNCH-7 | SAST/DAST | CI/ | 2 | Security |
| S4 | Security | LAUNCH-8 | Pen test | docs/ | 2 | Security |
| S4 | Deploy | LAUNCH-9 | Incident | docs/ | 1 | Ops |
| S4 | Deploy | LAUNCH-10 | Handoff | docs/ | 2 | Ops |
| S4 | Test | TEST-GAP-2* | Integration | usbvault-app/ | 3 | Testing |
| S4 | Docs | BUS-1* | Arch docs | docs/ | 2 | Docs |
| S4 | Security | DEP-1* | Supply chain | CI/ | 2 | Security |
| BL | Docs | DOC-1 | User guide | docs/ | 3 | Docs |
| BL | Docs | DOC-2 | API ref | docs/ | 2 | Docs |
| BL | Docs | DOC-3 | Admin manual | docs/ | 2 | Docs |
| BL | Test | TEST-1 | E2E suite | test/ | 4 | Testing |

* = NEW item from data plugin analysis

# Capacity Planning & Velocity

| Sprint | Planned Pts | Est. Velocity | Confidence |
| --- | --- | --- | --- |
| Sprint 1 | 26 | 26 | High — focused crypto |
| Sprint 2 | 24 | 24 | High — well-scoped |
| Sprint 3 | 32 | 28-32 | Medium — new items |
| Sprint 4 | 27 | 24-27 | Medium — integration tests |
| Total | 109 | 102-109 | Likely range |

Notes:

- Sprints 1-2: High confidence from proven velocity on architecture review.

- Sprint 3: New items are infrastructure work, lower uncertainty. TEST-2 upgrade reflects broader scope.

- Sprint 4: Integration test and supply chain work exploratory; may require mid-sprint adjustment.

# Dependencies & Sequencing

## Critical Path

- C-1, C-2 blockers for M-3 and TEST-2

- M-1, M-2, M-4 blockers for M-3 and CR-1

- USB-COMP-1, REPO-1 can proceed in parallel

- MONO-1 starts Sprint 3 week 2 after initial tests

- TEST-GAP-2 depends on CR-1, M-3, C-2; target Sprint 4 week 1

## External Dependencies

- OAuth Provider credentials — M-1 scope; coordinate early

- Penetration tester — LAUNCH-8 scope; book 6 weeks ahead

- Database host (staging) — needed by M-5; provision Sprint 2 week 1

# Post-Launch Backlog

Important items deferred past Sprint 4. Prioritize based on user feedback and operational load.

| ID | Task | Rationale | Est. | Area | Pri |
| --- | --- | --- | --- | --- | --- |
| DOC-1 | User guide | Expand post-launch | 3 pts | Docs | P1 |
| DOC-2 | API reference | Auto-gen; refine later | 2 pts | Docs | P2 |
| DOC-3 | Admin manual | Based on ops load | 2 pts | Docs | P2 |
| TEST-1 | E2E suite | Post-launch automation | 4 pts | Testing | P2 |
| PERF-1 | Optimization | Profile in staging | 3 pts | Perf | P2 |
| SCAL-1 | Multi-region | Single region first | 5 pts | Ops | P3 |
| AUDIT-1 | Audit replay | If demanded | 2 pts | Security | P3 |

Estimate: ~21 additional points; target Q3-Q4 2026 if product-market fit validated.

# Summary of Changes from Original Plan

## What Changed

- Sprint 3: +10 pts (22 → 32 pts). Added USB-COMP-1, MONO-1, I18N-1, REPO-1; TEST-2 upgrade 3 → 5 pts.

- Sprint 4: +7 pts (20 → 27 pts). Added TEST-GAP-2, BUS-1, DEP-1.

- Total: 98 → 109 pts (+11%).

- All new items tagged (NEW) for visibility.

## Why These Items Matter

- USB-COMP-1: 359 MB bloat unsustainable; must fix pre-launch.

- TEST-GAP: 1% frontend vs 72% backend is critical quality gap.

- MONO-1: Large files accelerate tech debt; refactoring prevents regressions.

- BUS-1: Single-author codebase is a knowledge concentration risk.

- DEP-1: 301 dependencies require supply chain hardening for security compliance.